FASTRAK MOBILE LAB

Local SEO  —  Rank #1 Strategy & Action Plan

Site: fastrakmobilelab.com     |     Prepared: June 7, 2026

# 1. Where Fastrak Stands Today

Ahrefs data pulled June 7, 2026 shows the full picture:

| Metric | Current Status |
| --- | --- |
| Domain Rating (DR) | 0.6 / 100 (essentially invisible to Google) |
| Referring Domains (live) | 174 |
| Ranked Keywords (US) | 1 keyword — position 95, zero traffic |
| Estimated Organic Traffic | 0 monthly visitors |
| #1 Target Keyword | "mobile phlebotomy near me" (vol 150, KD 30, traffic potential 1,000) |
| #2 Target Keyword | "paternity test atlanta" (vol 30, KD 0, traffic potential 150) |
| SERP Feature on ALL targets | Local Pack (Google Maps) — map results appear above organic |

KEY INSIGHT: Every target keyword triggers a Google Maps Local Pack above organic results. The map pack captures ~44% of all clicks. Winning the map pack — NOT organic position 1 — is what drives calls and bookings. Google Business Profile is the single highest-impact lever available right now.

# 2. Competitive Landscape

## 2.1  National Competitor — GetLabs (getlabs.com)

GetLabs is the dominant national mobile phlebotomy brand. Even with high domain authority, their organic results still lose clicks to the local pack. Fastrak cannot beat them nationally — but CAN beat them locally in Gwinnett County by owning the map pack:

| Keyword GetLabs Ranks For | Their Position | Monthly Volume | KD |
| --- | --- | --- | --- |
| mobile phlebotomy services | 3 | 450 | 8 |
| mobile phlebotomy | 3 | 1,200 | 24 |
| mobile phlebotomy near me | 5 | 150 | 30 |
| at home phlebotomy | 1 | 90 | 12 |
| phlebotomy services near me | 2 | 90 | 0 |
| home phlebotomy services near me | 3 | 40 | 6 |

## 2.2  Local Competitors (Gwinnett County)

Local individual phlebotomists, nursing agencies, and home health companies may appear in the Gwinnett map pack. They typically have low domain authority but may have more Google reviews — which is the key ranking factor in the local pack.

ACTION REQUIRED: Search "mobile phlebotomy near me" in Gwinnett County on a phone (logged out of Google). Note the 3 businesses in the map pack. Count their reviews. Fastrak needs to match then surpass their review count and rating to displace them.

# 3. The 5-Phase Rank #1 Plan

## PHASE 1 (Weeks 1-2): Google Business Profile Optimization

Impact: HIGHEST  |  Effort: Medium  |  Time to Results: 4-8 weeks

The local pack shows for 100% of Fastrak commercial target keywords. GBP directly controls whether Fastrak appears in that pack. This is the single most impactful SEO action.

### 1A. Business Profile Setup

- Business name: Fastrak Mobile Lab (exact match — no keyword stuffing in name)

- PhlebotomistPrimary category:

- Additional categories: Medical Laboratory, Drug Testing Service, Paternity Testing Service

- Service area: Set as a Service Area Business (not storefront). Add all service cities: Lawrenceville, Lilburn, Snellville, Grayson, Loganville, Duluth, Norcross, Tucker, Decatur, Stone Mountain, Conyers, Marietta, Sandy Springs, Buford, Suwanee, Gwinnett County

- Do NOT add a physical storefront address unless clients walk in to a location

### 1B. Business Description — Use All 750 Characters

Fastrak Mobile Lab is a licensed mobile phlebotomy service serving Gwinnett County and Metro Atlanta, GA. Our certified phlebotomists come to your home, office, or facility for blood draws — no lab visit required. We accept doctor requisitions and self-pay clients, delivering samples to LabCorp or Quest Diagnostics. We also offer mobile DNA and paternity testing and pre-employment drug testing (DOT and non-DOT). Ideal for elderly patients, people with disabilities, busy professionals, and assisted living facilities. Book online or call for same-day service.

### 1C. Services to List in GBP

- Mobile Phlebotomy / At-Home Blood Draw

- DNA Testing / Paternity Testing

- Pre-Employment Drug Testing

- DOT Drug Testing

- Corporate / Workplace Drug Screening

- Same-Day Blood Draw Service

- Lab Sample Collection and Transport to LabCorp or Quest Diagnostics

### 1D. Photos — Minimum 10, Target 20+

- Logo with white background

- Cover photo: phlebotomist with client in a home or office setting

- 3-5 action shots: blood draw procedure, sample handling, kit preparation

- Team/headshot photos

- Equipment photos

- Any certifications or license documents

### 1E. Pre-Populate the GBP Q&A Section

Questions submitted to Q&A are indexed by Google and appear in search. Add these proactively:

| Question | Answer to Post |
| --- | --- |
| Do you need a doctor's order? | We accept both doctor requisitions and self-pay orders for mobile blood draws throughout Gwinnett County and Metro Atlanta. |
| Do you serve assisted living facilities? | Yes. We regularly visit assisted living, memory care, and skilled nursing facilities in Gwinnett County and surrounding areas. |
| What labs do you deliver to? | We deliver samples to LabCorp and Quest Diagnostics based on your doctor's preference or your choice. |
| How fast can you come? | Same-day and next-day appointments are often available. Call (678) 562-5244 or book online to check current availability. |
| Do you do drug testing? | Yes. We offer pre-employment, DOT, and workplace drug testing at your location throughout Gwinnett County. |

## PHASE 1 (Continued): Reviews — #1 Local Pack Ranking Factor

Reviews are not optional. Google weights review quantity and rating more heavily than any other local pack factor. A competitor with 50 reviews will outrank Fastrak regardless of website quality. Target: 25 reviews with 4.8+ average within 60 days.

### Review Request Automation (Set Up in GHL)

- Trigger: appointment marked complete in GHL pipeline

- Delay: 2 hours after completion (experience still fresh)

- Channel: SMS (outperforms email for review requests)

- Message: "Hi [Name], thanks for choosing Fastrak Mobile Lab today! If you had a great experience, a quick Google review helps others find us — it takes 30 seconds: [GBP review link]. Thank you!"

- Follow-up: If no review after 3 days, send one email follow-up

- Respond to every review — positive and negative — within 24 hours

## PHASE 2 (Weeks 2-4): Complete Pending Technical SEO Fixes

Impact: MEDIUM  |  Effort: LOW (scripts already written)  |  Time to Results: 2-4 weeks

| # | Action | What It Fixes | Priority |
| --- | --- | --- | --- |
| 1 | Run tools\_fix_suwanee_duplicate_meta.py | Duplicate meta description on Suwanee page (Ahrefs Error level) | URGENT |
| 2 | Run tools\_fix_meta_length_and_duplicates.py | 6 city pages >155 char meta + 11 posts with Elementor duplicate meta | HIGH |
| 3 | Upload fastrak-correct-schema.php to wp-content/mu-plugins/ | Removes invalid serviceType + medicalSpecialty from global schema block, outputs correct MedicalBusiness schema | HIGH |
| 4 | Run tools\_fix_global_schema_errors.py | Patches bad schema if also stored in Rank Math post meta | MEDIUM |
| 5 | Add Service schema in Rank Math on each service page | Use templates in tools\_service_schema_templates.md — adds Service @type with serviceType per page | MEDIUM |

### How to Run the Scripts

- Open PowerShell or Command Prompt

- cd C:\Users\baysh\Fastrak Mobile Lab

- Run: python tools\_fix_suwanee_duplicate_meta.py

- Run: python tools\_fix_meta_length_and_duplicates.py

- Run: python tools\_fix_global_schema_errors.py

- For the mu-plugin: upload tools\_fix_global_schema_wordpress_snippet.php via WordPress admin File Manager or FTP. Place in wp-content/mu-plugins/. Rename to fastrak-correct-schema.php. MU plugins activate automatically.

## PHASE 3 (Weeks 3-8): City Page Content Overhaul

Impact: HIGH  |  Effort: High  |  Time to Results: 6-16 weeks

City pages are the organic ranking vehicle for "mobile phlebotomy [city] GA" queries. Thin or templated pages (same content, city name swapped) will not rank. Each page needs 600-1,000 words of unique, locally-relevant content.

### Content Standard Per City Page

- Minimum 600 words unique content (target 800-1,000)

- H1 must contain city name + service: "Mobile Phlebotomy in Lawrenceville, GA"

- City name used naturally 5-8 times in body copy — never forced

- Include neighborhood references, local context (e.g., "serving clients near Gwinnett Medical Center")

- Short FAQ section — 2-4 locally-relevant questions

- Embedded Google Map of service area

- Clear CTA: phone number + booking link, repeated at bottom

- Add Service schema in Rank Math Custom Schema using _service_schema_templates.md

### Keyword Targets by City Page

| City (Priority) | Primary Target Keyword | Secondary Keywords | Focus Service |
| --- | --- | --- | --- |
| Lawrenceville (1) | mobile phlebotomy lawrenceville ga | blood draw lawrenceville, at home lab test lawrenceville | Phlebotomy + Drug Test |
| Lilburn (2) | mobile phlebotomy lilburn ga | home blood draw lilburn, phlebotomist lilburn | Phlebotomy |
| Snellville (3) | mobile phlebotomy snellville ga | blood draw at home snellville, lab services snellville | Phlebotomy + DNA Test |
| Grayson (4) | mobile phlebotomy grayson ga | mobile blood draw grayson, at home phlebotomy grayson | Phlebotomy |
| Loganville (5) | mobile phlebotomy loganville ga | blood draw loganville ga, phlebotomist loganville | Phlebotomy |
| Duluth (6) | mobile phlebotomy duluth ga | home lab draw duluth, corporate blood draw duluth | Phlebotomy + Corporate |
| Norcross (7) | mobile phlebotomy norcross ga | at home blood draw norcross | Phlebotomy |

### City Page Template Structure

| Section | Content |
| --- | --- |
| H1 | Mobile Phlebotomy in [City], GA — Blood Draws at Your Location |
| Opening paragraph | What Fastrak does, who it serves, that it specifically serves [City] |
| H2: Services in [City] | Mobile Blood Draw, DNA Testing, Drug Testing — 2-3 sentences each |
| H2: How It Works | 3-step: Book → Phlebotomist Arrives → Sample Delivered to Lab |
| H2: Who We Serve | Elderly, disabled, busy professionals, assisted living, corporate clients in [City] |
| H2: Service Area | Mention [City] zip codes, neighborhoods, nearby areas also covered |
| H2: FAQ | 2-4 questions locally specific to [City] (e.g., "Do you serve [City] assisted living?") |
| CTA Section | Bold phone number + Book Now button. Repeat city name. Last thing on page. |

## PHASE 4 (Weeks 3-12): Local Citations — NAP Consistency

Impact: MEDIUM  |  Effort: Medium  |  Time to Results: 8-16 weeks

Citations are external mentions of Fastrak's name, address, and phone (NAP). Google uses them to verify the business is real and confirm its service area. Inconsistent NAP = suppressed rankings.

### Canonical NAP — Use This Everywhere, Always

Business Name: Fastrak Mobile Lab Phone: (678) 562-5244 Address: 2330 Scenic Hwy S, Snellville, GA 30078 Website: https://fastrakmobilelab.com

### Citation Build List

| Directory | URL | Type | Week |
| --- | --- | --- | --- |
| Google Business Profile | business.google.com | Maps | Done |
| Yelp | biz.yelp.com | General | 1-2 |
| Facebook Business | business.facebook.com | Social | 1-2 |
| Apple Maps | mapsconnect.apple.com | Maps | 1-2 |
| Bing Places | bingplaces.com | Maps | 1-2 |
| Healthgrades | healthgrades.com | Medical | 2-3 |
| Zocdoc | zocdoc.com | Medical | 2-3 |
| Better Business Bureau | bbb.org | Business | 2-3 |
| Yellow Pages | yellowpages.com | General | 2-3 |
| Nextdoor for Business | nextdoor.com/for-businesses | Hyper-local | 2-3 |
| Thumbtack | thumbtack.com | Service | 3-4 |
| Foursquare | foursquare.com | General | 3-4 |
| MapQuest | mapquest.com | Maps | 3-4 |
| Gwinnett Chamber of Commerce | gwinnettchamber.org | Local Org | 4 |
| Expertise.com | expertise.com | Medical | 4 |
| SeniorAdvisor.com | senioradvisor.com | Senior Care | 4-5 |
| Caring.com | caring.com | Senior Care | 4-5 |

## PHASE 5 (Months 2-6): Blog Content & Backlinks

Impact: HIGH long-term  |  Effort: High  |  Time to Results: 3-9 months

With DR 0.6, Fastrak needs backlinks to build domain trust. Backlinks are the primary factor separating page 1 from page 5 in organic results below the local pack. Simultaneously, blog content attracts informational searches that convert to bookings.

### 5A. Blog Content — Articles to Publish

| Article Title + Target Keyword | Search Intent | Length | Priority |
| --- | --- | --- | --- |
| "Can a Phlebotomist Come to My Home?" | Informational | 800 words | HIGH |
| "What to Expect from a Mobile Blood Draw" | Informational | 800 words | HIGH |
| "Mobile Phlebotomy for Elderly Patients" | Informational | 800 words | HIGH |
| "Mobile Blood Draw vs. Walk-In Lab: Which Is Right?" | Commercial | 800 words | HIGH |
| "How to Read Your Blood Test Results" | Informational | 1,000 words | MEDIUM |
| "Pre-Employment Drug Testing: What to Expect" | Informational | 800 words | MEDIUM |
| "DNA Paternity Test Without Father's Consent in Georgia" | Informational | 800 words | MEDIUM |
| "LabCorp vs Quest Diagnostics: What's the Difference?" | Commercial | 1,000 words | MEDIUM |

Every article should end with: "Book a Mobile Blood Draw in Gwinnett County" — CTA with phone number and booking link. This converts informational readers into leads.

### 5B. Backlink Sources to Target

| Source | Tactic | Difficulty |
| --- | --- | --- |
| Gwinnett Chamber | Join as member — directory listing + newsletter mention | Easy |
| Senior Care Directories | SeniorAdvisor.com, Caring.com — both accept service businesses | Easy |
| Assisted Living Facilities | Offer to be preferred mobile draw provider. Some will add a link on their patient resources page. | Medium |
| Local Doctor Offices | Provide a patient handout. Some will link to Fastrak on their "helpful resources" page. | Medium |
| Press Release | Submit to PRWeb/BusinessWire — "Gwinnett mobile phlebotomy service launches same-day appointments" | Easy |
| Gwinnett Daily Post | Pitch a local health/business story to the editor. Local news links are high-value. | Hard |
| HARO / Connectively | Respond to healthcare and local business journalist queries for editorial links | Medium |

# 4. Execution Timeline

| When | Phase | Actions |
| --- | --- | --- |
| Week 1 | GBP + Technical | Complete GBP profile fully. Set up review request SMS automation in GHL. Run _fix_suwanee_duplicate_meta.py and _fix_meta_length_and_duplicates.py. Upload mu-plugin schema fix. |
| Week 2 | GBP + Citations | Request reviews from all past clients. Build Tier 1 citations: Yelp, Facebook, Apple Maps, Bing Places. Run _fix_global_schema_errors.py. |
| Weeks 3-4 | Content + Citations | Rewrite Lawrenceville and Lilburn city pages (800+ words each). Add Service schema via Rank Math. Build Tier 2 citations: Healthgrades, BBB, Yellow Pages, Nextdoor, Gwinnett Chamber. |
| Weeks 5-8 | Content + Backlinks | Rewrite Snellville, Grayson, Loganville pages. Publish first 3 blog posts. Begin outreach to doctor offices and assisted living facilities. Submit press release. |
| Month 3 | Content + Backlinks | Complete Duluth, Norcross pages. Publish 2 more blog posts. Follow up on backlink outreach. Goal: 25+ GBP reviews by end of month. |
| Month 4-6 | Ongoing | Monthly: 1-2 new blog posts, 1-2 new backlinks, respond to all reviews, post to GBP weekly (Google Posts: new offers, service updates, team news). |

# 5. Realistic Expectations

Local SEO takes time. The timeline below assumes consistent execution. Skipping reviews or GBP optimization will significantly delay all other results.

| Milestone | Expected Outcome |
| --- | --- |
| Month 1 | GBP appears for branded searches. With first 5-10 reviews, begin appearing in map pack for some Gwinnett city-specific searches. |
| Month 2-3 | 10-15 organic keywords ranking (positions 20-50). 25+ GBP reviews — competitive for local pack top 3 in primary service cities. |
| Month 3-4 | Consistent local pack appearances for "mobile phlebotomy [city] GA" queries. Organic positions improving as backlinks accumulate. Inbound calls increasing. |
| Month 4-6 | Local pack top 3 for Gwinnett-area queries. Organic page 1 for city-specific service keywords. Measurable increase in bookings from search. |
| Month 6-12 | Local pack #1 for priority Gwinnett keywords. Organic page 1 for 20-30 keywords. Domain Rating reaches 5-15 with continued backlink work. |

# 6. Monthly Metrics to Track

| Metric | Where to Check | Target |
| --- | --- | --- |
| GBP Impressions (map views) | GBP > Performance | Growing month-over-month |
| GBP Calls from Search | GBP > Performance > Calls | 5+ calls/month by Month 2 |
| GBP Review Count & Rating | Google Business Profile | 25+ reviews, 4.8+ by Month 3 |
| Ranked Keywords | Ahrefs > Site Explorer | 20+ by Month 4 |
| Organic Traffic | Ahrefs or Google Search Console | 50+ monthly by Month 4 |
| Domain Rating | Ahrefs > Site Explorer | 5+ by Month 6 |
| Local Pack Position | Search on phone (logged out) in Snellville | Top 3 by Month 4-6 |
| Citations Built | BrightLocal or manual count | 15+ by Month 1, 30+ by Month 3 |

Bottom line: The path to #1 runs through Google Business Profile first. Reviews drive the map pack. City page content + backlinks drive organic. Schema fixes remove technical errors. Do them in that order. With consistent execution, Fastrak can own the local pack for Gwinnett County mobile phlebotomy searches within 90-120 days.